## 1st RA Bill
C.P.W.A. - 26 Revised
DELHI DEVELOPMENT AUTHORITY
RUNNING ACCOUNT BILL
(Referred ot in Paragraphs 10-2-10 and 10-2-12)
(Final payments must in variably be made on form printed on yellow paper which should not be used for intermediate payments for contractor. This form provide for in (1) advance payments and (2) Payments for Measured Works. The form of Secured advance which has been printed separately attached where necessary)
Division : Sports Wing |  |  |  |  | Sub/Division : |  | DGCD,DDA
Cash Book Voucher No : …………………………………………………………………………………….. | [6 empty] | Dated : ……………………………………..
Name of the Contractor : M/s High Command
Name of Work : M/o Dwarka Golf Course, Sector-24 | [9 empty] | .
Sub Head: Providing various staff for office maintenance at Dwarka Golf Course.
Serial No. of this Bill : 4th R/A Bill
No. and date of the Previous bill of this work : ${office_bill_no}
Reference in Agreement No. : 01/DWGC/DDA/2024-25
Date of written order to commence work : 01.06.2025
Date of completion of work : work under progress
Account of Work Executed
Item of Works Grouped under Sub-work of Estimated | Unit | Rate |  | Quantity Executed Up to date as per Measurement Book | Payment on the Basis of Actual Measurement |  |  |  | Remarks
[5 empty] | Up to date |  | Since Previous Bill
1 | 2 | 3 |  | 4 | 5 |  | 6 |  | 7
|  | Period : | 01.10.2025 to 30.11.2025 (Two Months)
Recoveries on :
Carried over
2
Item of Works Grouped under Sub-work of Estimated | Unit | Rate |  | Quantity Executed Up to date as per Measurement Book | Payment on the Basis of Actual Measurement |  |  |  | Remarks
[5 empty] | Up to date |  | Since Previous Bill
1 | 2 | 3 |  | 4 | 5 |  | 6 |  | 7
Certified that :
1. The work has been carried out as per Terms & Conditions of agreement and as per the directions of Secretary (DGCD). 2. The amount paid to the agency by this office in this bill tallies with bank statement providided by the agency. 3. All necessary recoveries has been made. 4. No minor labour was engaged at site. 5. No labour complaint has been received. 6. All payment made to the staff through bank transfer. 7. Forninghtly labour report submitted by the agency.
| Secretary, DGCD, DDA | [5 empty] | RE (Civil) DGCD, DDA
Total value of work done to date (A):
Deduct valueof work shown in previous bill:
Net value of works since Previous bill (F) :
Figure (F) in words Rupees :
N.B.- When there are two or more entries in column 6 relating to each sub-head of estimate they should in the case of works the accounts of which are kept by sub-head be totalled and the total recorded in column 7 for posting the works abstract.
II Certificate & Signature
1. The measurement of which are based the entries the column 1 to 6 of account I, were made by Sh. Deepak Sharma, RE (C)
on / / and are recorded as page to of Measurement Book No.
2. Certified that in addition to and quite apart from the quantities to work actually executed as shown in column 4 of the Account 1, some work has actually been done in connection with several items and the value of such work (after deducting therefrom proportionate amount of secured advances if any ultimately recoverable on account of the quantities of the materials used therein) is in no case less than the advance payments as per item 2 of the memorandum if payments made or proposed to be made, for the convenience of the contractor, in anticipation and subject to the result of detailed measurements, which will be made as soon as possible.
[5 empty] | Dated Signature of officer |  |  | (……………….…………………..)
[5 empty] | Preparing the Bill |  |  | RE(CIVIL), DGCD, DDA
[5 empty] | *Dated Signature of Officer (…..……..….……….…..……..) |  |  | (……………….…………………..)
Date Signature of contractor |  |  |  |  | Authorising payment |  |  | Secretary, DGCD, DDA
** This certificate must be signed by Sub-Divisional Officer.
* This Signature is necessary only when the officer who prepares the bill is not the officer who authorises the payment. In
such a case two signature are essential.
3
III. MEMORANDUM OF PAYMENT
1. Total value of work actually measured, as per Actt. 1, Cy 1.5 Entry (A)………………………………. | [8 empty] | Rs. | P.
2. Total “up to date” advance payments for work not yet measured, as per details given below: -
(a) Total as per previous bill ………………………………………………
(b) Since previous bill ……………………………………………… as per page …………………………. Of
M.B. No ……………………………….
3. Total “up to date” secured advances on security of materials, as per Annexure (Form 26-A)
Col. 8, Entry……….(C)
4. Total (Item 1+2+3) ……………………………………………………………………………………………………………
5. Deduct, amount withhold: -
[6 empty] | Rs. P. |  | 5
Figures for Works Abstract
a) From privious bill as per last Running Account
Rs. P. | Bill …………….
b) From this bill …………………………………..
6. Balance, I.e. "up to date" payment (Items 4 - 3) …….…………………..…(K)*
7. Total amount of payment already made as per entry (K) of
last Running Account Bill No …………… of ………………………
forwarded with accounts for ……………..20…………………….
8. Payments now to be made, as detailed below: -
|  | By recovery amounts conditable to this works |  |  |  |  | Rs. P. | 8
(a)
Total 5 (b) + 8 (a) …………………………………………………(G)
By recovery amounts creditable to other
works or heads of accounts ----
| (b) | (i) Income tax Recovery @ 2 %
(ii) Security @ 5 %
(iii) CGST @ 1 %
(iv) SGST @ 1 %
|  | (v) Withheld non-payment of wages | [8 empty] | (v) Withheld on a/c of non-payment of wages
(c) By cheque …………………………………………………………
Total 8 (b) + (c) ………………………… (H) ……………………….
Pay RS. * …………………………………………………………………………………………………………………………………………………………………………
………………………………………………………………………………………………………………………………………………………………………………………..
……………………………………………………………………………………………………………………………………………………………... '@ (by cheque)
Dated initials of Disbursing Officer
Received Rs. ≈ ≈ ………………………………………………………………………………………………………………………………………………………………
………………………………………………………………………………………………………………………………………………………………………………………
…………………. as per above memorandum on account of this work. | [7 empty] | (Amount in vernacular)
Stamp
Dated the ……………………………20……….
** Witness …………………………………………………… | [7 empty] | Signature of Contractor
Paid by me, vide cheque No………………………………………… dated ………………………… 20……
4
IV - Remarks
* This figure should be tested to see that it agrees with the total of item 7 and 8
this entry being already suitable and the alteration attested by dated initials.
@Here specialy the net amount payable, vide Item (C) .
≈ ≈ The payees acknowledgement should be for the gross amount paid as per Item i.e., (a8+b+c)
** Payment should be attested by some known person when the payee's acknowldgement is given by a mark, seal or thumb
Impression.
This space is reserved for any remarks which the Disbursing Officer or the Divisional Officer may wish to record in respect on
the execution of the work check of measurement or the state of contractor's amount
FOR USE IN DIVISIONAL OFFICE
Accounts |  |  |  | Checked |  |  |  | Divisional
Clerk | [8 empty] | Accountants
FOR USE IN AUDIT OFFICE
Computerd |  |  |  | Classification |  |  |  |  | Revised
Checked
Checked with schedule |  |  |  | Reviewed
of rates/checked with
rates as per agreement
Auditor |  |  |  | Superintandent |  |  |  |  | Gazetted Officer